## questions (1)
Explain the process of communication based on trying to undestand better what was said or writen. | Analyze | Teamwork | East | FALSE | FALSE
What does an Escalation Plan contain | priorities and solutions | Priorities | East | FALSE | FALSE
What is the first thing you do in the Communication management? | planning | Second step is implementation | North | FALSE | FALSE
What is the last step of Communication control? | feedback | Third step is Assessment | East | FALSE | FALSE
Complete the following definition: the verb risk means to expose someone or something to hazzard or ... | danger | Combination between the probability of producing a event and consequences it | South | FALSE | FALSE
Which are the type of entries in the process of risk identification? | internal external | Identifying risks is the process through which possible risks that may affect the smooth development of the project are identified and documented. | West | FALSE | FALSE
A graphical identifying risks technique | Pareto | Pareto chart | East | FALSE | FALSE
Give me an example of a source of risk that comes from the physical space and involves buildings and strees to be filled with water. | flood | water overflows onto land that is normally dry | East | FALSE | FALSE
What is the name of a source of risk that comes from the The political environment that involves and active or passive abuse for the purpose of obtaining financial advantages. | corruption | Romanian Politicians | East | FALSE | FALSE
What is the name of the technique utilised in Quantification / analysis risks to calculate costs. | Monte-Carlo | Monte Carlo simulation | East | FALSE | FALSE
What is the most used method to simulate risks? | Monte-Carlo | Popular Betting spot in Monaco | North | FALSE | FALSE
What is the name of the process in which you find a risk to be tolerable. | risk acceptance | accepting risk | West | FALSE | FALSE
A risk response control technique involving improvisation? | work around | work around | North | FALSE | FALSE
Who is responsible for communicating with shareholders? | the manager | The person responsible for the activity of a group | West | FALSE | FALSE
What is the process of hiring and attracting those interested in applying for various positions called? | recruitment | Synonym with: selection. | North | FALSE | FALSE
What is the final stage of decision-making in the recruitment process? | selection | Synonym with: sorting | East | FALSE | FALSE
The communication strategy comes in multiple stages such as: Formulating the message Planning and organizing etc. What is the first stage of the communication strategy called? | identifying objectives | Identifying (...) | South | FALSE | FALSE
Who is funding the project ? | the sponsor | Physical person with the quality of sponsoring someone or something | East | FALSE | FALSE
What is the group responsible for reviewing technical specifications and authorizing changes? | the management staff | Belongs to the registry of stakeholders | North | FALSE | FALSE
Who is the beneficiary of a project? | the client | The one who buys | West | FALSE | FALSE
Who ensures that the technical part of the project is well-executed? | the technical leader | The person chosen by a team | West | FALSE | FALSE
What is the name of the tool that includes details about communication within a project and the person responsible for this communication? | the communication matrix | Represents an easy way to keep stakeholders informed | South | FALSE | FALSE
What is the hierarchical structure that enhances the understanding of the communication process called? | the communication flowchart | A visual diagram | South | FALSE | FALSE
What concept is represented by a strategic approach to the efficient management of people in a company or organization? | human resource management | The structure in the company that is of particular importance at the organizational and personal level | East | FALSE | TRUE
Note on B1: abc: mai degraba "explain the process of communication"
Note on A5: abc: Nu aceasta este definitia unui risc… De modificat
Note on A6: abc: reformulare: "which are the types of entries in the process of risk'identification?
Note on A8: abc: prea vag. De reformulat
Note on A9: abc: idem
Note on A13: abc: reformulat: "A risk response control technique involving improvisation."
Note on A14: abc: reformulat: "Who is responsible for communicating with stakeholders?"
Note on A15: abc: reformulare: What is the process of hiring, identifying and attracting those interested in applying for various positions in a company called?